## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Not being able to navigate and produce a working LCD task because I did not complete project 7 | 20 | 70 | 1400 | 2023-03-20 | 2023-04-03 | O | Gaining a stong understanding of the project at the beginning. Using spring break to understanding the provided project 7.
Physics task funciionality. A majority of the project is contingent on this task working. | 8 | 70 | 560 | 2023-03-20 | 2023-04-03 | O | Unit testing at every level of functionality, creating a flow chart for the task, and starting early.
0
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100