## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Not being able to navigate and produce a working LCD task because I did not complete project 7 | 20 | 70 | 1400 | 2023-03-20 | 2023-04-03 | O | Was not able to get provided lab 7 to work over break. I have since then fixed the include issue and I am exploring the issue.
Physics task funciionality. A majority of the project is contingent on this task working. | 8 | 40 | 320 | 2023-03-20 | 2023-04-05 | M | Had a thorough converstation with Jon about the physics task as a whole and have more confidence in being able to implementing the task
LED Task | 20 | 70 | 1400 | 2023-04-04 | 2023-04-08 | M | This might be a simple task that I might complicate. I will make sure this doesn’t derail progress by leaving it last since it doesn’t inhibit game play functionality
Not Being able to attend office hours | 70 | 40 | 2800 | 2023-04-13 | 2023-04-14 | O | I have class during Will's office hours and I think it makes it difficult to get hands one help throughout the week. I try to resolve this by looking to see similar problems are solved on slack and Jon's availability before class
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100